EVALUATION PLAN

Contents

Terms of Reference	3

Aims of the evaluation plan (WP7)	3

Overall Methodology	4

What will be evaluated	4

Questions to be answered through the evaluation	5

Time-frame for the evaluation	5

Conclusion	6

Appendix 1: Individual work packages	7

Work package 1: Project analyses	7

Work package 2: CCeD method adaptation	7

Work package 3: CCeD work sessions	7

Work package 4: Language and cultural adaptations	7

Work package 5: VET teacher training courses using Vitae	8

Work package 6: Establish a Community of Practice for VET teacher training	8

Work package 7: Evaluation	9

Work package 8: A generic business model	9

Work package 9: Dissemination and exploitation	10

Work package 10: Project management	10

Appendix 2: Evaluation of the Trondheim kick-off meeting 13-14 December 2010	11

Issues for attention are few	11

Summary of 14 responses	12

Appendix 3:  Some early WP results – the example of WP 10	22

Contracts:	22

Project web site:	22

Partner meetings:	22

Net meetings:	22

Accounting:	23

Plan for evaluation in the Understand IT project

This document describes the way in which evaluation will be undertaken in the UnderstandIT project.

Terms of Reference

- Aims of the evaluation plan (WP7)

The aim of the evaluation plan is to establish efficient procedures for monitoring the project process, to ensure quality control of the project results as well as an evaluation of the project process and project results.

The Evaluation will therefore be qualitative and ongoing from the beginning. The evaluation report will be worked out step by step and follow the whole process.

Role & tasks of partners involved: The aims and methods of the evaluation plan are described in general terms in the original application for funding. Partners will present a plan of how to evaluate the work done in the work packages for which they were responsible and how to report back on it. The plan will be discussed by the project partners and a final plan will be agreed upon.

Role and tasks of the WP leader: The WP leader will:

- Assist the project coordinator in drafting a plan for the evaluation of the work done in each work package, the project results, and the project process. This plan will be presented to the other project partners at seminar 1, and a final version will be agreed on.

- be responsible for collecting the relevant evaluation data from the project partners during the project process, and in case of non delivery from a partner, alert the project coordinator

- assist in making the interim report

- assist in making an evaluation report at the end of the project

| Working methods and techniques | Work package leaders will form a quality management team who meet regularly online to implement the quality control plan. The plan will be discussed by the project partners and a final plan will be agreed upon. The project coordinator will collate results and potential consequences and make adjustments as necessary in consultation with the work package leaders. |
| --- | --- |
| Expected outcomes/results | Working with the WP leader, the other project partners will include the project process monitoring in the project work, adjust according to the project plans, and evaluate project deliveries. Expected results are: Project evaluation, interim report, final report |
| Quality management tools | The quality management team will apply tools, methods and concepts of the following standards and guidelines: - The “Survival Kit for European Project Management” (www.sokrates.at/survivalkit, 2001), which incorporates the experiences of a number of coordinators and evaluators of European projects. - The “Handbook Virtual Teamwork, making cooperation work in Leonardo da Vinci projects Information, theory and practical Tips”, published by the National Agency Leonardo da Vinci -The Netherlands 2004. Questionnaires, interview frames, focus group interviews, desk research, field research, quality management tool in e-learning developed by German partner Inter.research. |

Overall Methodology

Three main sources of guidelines have been used In the preparation of this evaluation plan.

Evaluation of the main work of the UnderstandIT project is embedded within the experimental methodology of both the Concurrent Design approach and the Business Model Generator approach. This integrated approach to the design of a business model for up-skilling VET teachers in the area of ICT integration includes paying attention to the design of the training, the marketing of the training to relevant decision-makers, ensuring correct pricing and evaluation of the training by the course participants.  This builds on, for example, the approach proposed in the PAS 1032-1 Process model for evaluating e-learning which was also a way of evaluating e-learning products over the whole process from conception to implementation  but which was never widely adopted  as it was presented in  a demanding  administrative way which was viewed as a heavy additional burden. So in theory, evaluation is now embedded into the UnderstandIT project as feedback and correction mechanisms are built into the CceD  and BMG methodologies.  Nevertheless evaluation instruments still need to be chosen and targets identified.

The novel elements of the project which particularly need to be evaluated are:

- implementing CCeD online

- packaging the  training  product according to the application of the Business Model Generator approach

Work Package leaders have produced targets but these will be supplemented by on-going qualitative evaluation at the end of every face to face meeting and every online meeting. The types of evaluation undertaken will be discussed with each WP leader.

Eg In work package 3 the post-session questionnaire was described in the following way:

Introduction

The purpose of this document is to collect information regarding questions which we want to use

in the survey after session one (WP03) in the UnderstandIT project.

Question categories

Category 1 - Closed questions with the Likert scale

We propose to use the Likert Scale with the following intervals for closed questions: (1) strongly

agree, (2) agree, (3) neutral (neither agree nor disagree), (4) disagree and (5) strongly disagree.

Category 2 - Like category 1 pluss the N/A alternative

(1) strongly agree, (2) agree, (3) neutral (neither agree nor disagree), (4) disagree, (5) strongly

disagree and (6) (N/A). The sixth alternative (NA) would typically be used for the Business Plan

Team members, when we ask questions concerning the Vitea Course Team.

Category 3 - Open questions with free text

We propose to use some open questions with free text. Participants can write freely when

answering questions in this category.

- What will be evaluated

There are four main areas to be evaluated:

- Project management

- Transfer of the CCeD method to online  implementation

- Development of a generally applicable business model for VET training

- Transferability of the VITAE approach as a coaching model

It should be noted that the transfer of the CCeD process online and development of a business model for VET training such as VITAE are research exercises and therefore focus will be on the process more than the results initially.

- Questions to be answered through the evaluation

The overall aim of the project is to find an effective way of disseminating VET training, such as the VITAE approach, by devising a viable business model using the CCeD methodology transferred to the online medium.

Project management: Questions to be answered will be the universally applicable ones about competent organization, efficient communication internally between project partners and externally to relevant target groups, sound financial management and the promotion of a good working relationship between the partners.

CCeD Online: The main question to be answered in this area is whether it is practical to transfer the CCeD process to an online environment. Evaluation will look at whether the procedure implemented by the project is feasible and if not, then how, in concrete terms, it could be improved.

VET training business model: The question to be evaluated is whether the business model generator approach can be used to develop a viable business model in the VET training sector. We will also be looking at whether the model generated as a result of using the business model generator approach helps to disseminate adoption of a VET training product, in this case the VITAE approach. In the project there will not be time / activities to try out and evaluate the Generic BP. We have planned to go through the following steps to come to the GBP:

- CCeD method (with maybe 4 different versions of the BP as a result)

- WP5 – trials and evaluation

- WP 8 – ”Construction” of the GBP based on the 4 models and the evaluation results.
The resulting GBP will be a framework/pattern that can be used later by other projects etc, and not directly in Understand IT. (More or less like the Vitae approach document)

The VITAE coaching approach: How effective has the project been in communicating the VITAE approach to those project partners who were not part of the original project team and to relevant stakeholders and potential course participants. How has the VITAE approach benefited from a change of emphasis from mentoring which implies longer term support by an experienced person to an inexperienced person, to coaching which can be shorter term and more focused on concrete results and involve two-way peer coaching? Ie. Sometimes you know more than me and sometimes I know more than you.

- Time-frame for the evaluation

Evaluation will be ongoing throughout the life of the project starting with the kick-off meeting. In that way, significant deviations from the planned timetable and objectives can be identified and dealt with swiftly.

The gray cells in the GANTT chart below show the expected activity in each work package according to the original application.

It will be relevant to evaluate progress just before the interim report is due in September 2011 and then again prior to the final report. For the mid-term evaluation attention will focus on the CCeD process, both its adaptation and the online work sessions. The first two face to face meetings will also be evaluated as well as project management in general. In the second major evaluation the focus will be on the VITAE course pilots, CoP, the business model generator and dissemination.

- Conclusion

Plans are in place to evaluate this project in a timely manner. Experience so far in this early stage of the project shows a willingness by the project partners to participate in the evaluation activities and if this continues then this will ensure that all relevant stakeholders can be kept informed about the progress of the project and can expect that remedial action could be taken in time if it proves to be necessary.

In preparing this evaluation plan all Work Package leaders have been through a process of prior planning of the evaluation process and continued dialogue between WP leaders and myself as leader of the evaluation WP should ensure that we maintain a coherent approach to evaluation within the project as a whole.

The overall success of the project will be evaluated according to whether the updated pilot courses as presented by the newly developed business model:

Are seen as clearly beneficial by VET management

Have increased participants’ confidence in integrating ICT in their everyday teaching

Enable participants to help colleagues achieve the same confidence

Appendix 1: Individual work packages

- Work package 1: Project analyses

Aims: Learn from and about the results from all the involved projects. The projects to be analysed are the Leonardo projects VITAE, iQTool and eTutors Portal.

Expected outcomes: A Fact sheets about the

- VITAE project with references to online and other resources

- iQTool project with references to online and other resources

- eTutor Portal project with references to online and other resources

Quality management tools: Feedback from the Understand IT project partners

Quality indicators: Fact sheets produced by agreed deadlines which are accurate and understandable.

The fact sheet allows partners not part of the original project team to understand the project results and their use/consequences in/for the UnderstandIT project

- Work package 2: CCeD method adaptation

Aims: Learn how to use the CCeD method and adapt the method to the aims and objectives of the understand IT project.

Working methods: The CCeD method

Expected outcomes: A CCeD process description adapted to the Understand IT project, developed collaboratively using Google Docs, (a development of the Mindmap framework) to be used to transfer the Vitae results to new usergroups

Quality management tools: The CCeD process includes evaluation as an embedded part of the process. Note also that this is a research exercise where the process will be more in focus than the results.

- Work package 3: CCeD work sessions

Aims:

To further develop the the Vitae methodology and the Vitae courses.

To use the iQTool QAS tool to secure the content and activities planned for in Vitae.

To make preparation for creating a sustainable business model (WP8) to spread the results (Transfer of innovation) from the Vitae project to new institutions and new countries in Europe.

Working methods: CCeD method

Expected Outcomes:

A design document for Vitae, using iQTool for QAS and eTutor Portal as a repository.

A Business Plan for running Vitae courses in four institutions, in four European countries, with different EDU market situations

A set of evaluation reports

Quality management tools: 
A set of evaluation reports. Note also that this is a research exercise where the process will be more in focus than the results.

- Work package 4: Language and cultural adaptations

Aims: find ways of making the Vitae approach and training material available in different languages.

Working methods: The Vitae approach is based on Experience based learning.

There is only a small amount of learning material available for the course. Actually it is the VET teachers, trainers and tutors following the course who, by their collaboration in the course, define learning outcomes, develop learning activities, select relevant learning resources and technology for their own courses. (A social constructivist and learning by doing approach).

This means that there is only a small amount of learning material and resources to be translated.

However the Vitae approach in itself must be available in all the four languages.

Another activity is to experiment with automated translation. A candidate for this work is the Google Translate application. We will try out how this tool can be used as a part of cross national tutoring and mentoring.

The research foundation TISIP will translate material into Norwegian.

Expected Outcomes: A package for Vitae courses in four different languages.

- take into account language and cultural aspects (to be further developed during the project / CCeD sessions)
- base quality criteria  on outcome of CCeD sessions/ integrate the preparation of the decision on quality criteria into the sessions  (including the question what exactly shall be translated)
- make sure that language becomes not a barrier for mutual learning among the project partners (access to material, learning scenarios of pilot courses)
- take into account language/communication requirements of the (nature of the) CoP 
Quality management tools: Questions related to this will be included in the evaluation process of the course pilots.

- Work package 5: VET teacher training courses using Vitae

Aims: To increase the use of modern web 2.0 based ICT tools by VET teachers, trainers and tutors.

Run training courses in Portugal, Norway, Italy and Lithuania

Working methods: For this activity it is not only to run a course, using a member from the understand IT group as teacher, but rather try out how to organise a complete implementation of the course by the institutions involved.

In each institution there will be:

A) A formal approval of the course by the management

B) The announcement of the course

C) Involvement of the student administration for billing, student registration etc

D) Involvement of technicians for setting up equipment and software services

E) Involvement of teacher, trainers and tutors

F) Preparation before the course is run

G) Running the course

H) Creating a European dimension of the course by letting the "students" collaborate with each other

across the four countries, using automated translation.

I) Evaluating how it all worked, as seen from each involved actor

Expected outcomes:

Vitae courses

A set of evaluation reports

Quality management tools:

A common end of course questionnaire with country adaptations for participants, trainers and management.

- Work package 6: Establish a Community of Practice for VET teacher training

Aims: to establish a Web 2.0 workspace where VET teachers, tutors and trainers can exchange ideas. This forum could either be created as part of the project or it could be implemented as an activity within an ongoing CoP.

Working methods: Build on existing good practices

Expected outcomes: A CoP for sharing and reuse of resources, expertise

Quality indicators: # of participants, balanced with their activity; in this we would rely primarily on the outcomes from the vitae courses (since students in those courses should be into the cop, and the topics 
for discussion - at least in a bootstrap period) would come from the course activity;

Quality management tools:

usual techniques of analysis could be applied, by using some of the 
following data
         * Number of page views
         * Number of unique visitors
         * Number of new and return visitors
         * Number of pages viewed per visit
         * Number of times a visitor visits the site
         * Number of page views by content area

a questionnaire could be administered, to gather general data, such as 
     * Demographics
     * How users discovered the website
     * How often they access the website
     * Usefulness of the information
     * Other sources of information used
     * How they rate the ease of use (participate)
     * How they rate the ability to establish connections
     * How they rate the structure (hierarchy) of the community
     * Self-reported knowledge changes (one or two-questions)
     * Self-reported behavior changes (one or two-questions)
augmented with questions about some more specific (to the actual cop) topics, should a reasonable need for that arise

Also the structure of the cop could be used to gather data; for example, if we manage to have ratings (agreement/usefulness) from the users over the other user's contributions, we could infer data about 
participation and "satisfaction" (however, such specific features are to be discussed and decided in the design phase)

- Work package 7: Evaluation

Aims: establish efficient procedures for monitoring the project process, to ensure quality control of the project results as well as an evaluation of the project process and project results.

The Evaluation should therefore be qualitative and ongoing from the beginning. The evaluation report should be worked out step by step and follow the whole process.

Working methods: see top of document

Expected outcomes: A set of evaluation reports

Quality indicators:

Significant deviations are identified in a timely fashion and communicated to the project manager.

The project group has a clear idea about whether they are meeting the project objectives.

There is sufficient material for relevant external stakeholders, such as the funding agency, to know that what the project network has done has been evaluated and responded to by the project team.

Quality management tools: A structured series of questionnaires and moderated discussions will used as part of each meeting whether face to face or online. This document also details in Appendix 1 the strategies to be used to evaluate the outcomes in the individual work packages.

- Work package 8: A generic business model

Aims: to develop a generic business model, i.e.. a Pattern that can be used by other organizations who will implement the Vitae approach and by similar projects.

Working methods: We will use the handbook written by Alexander Osterwalder & Yves Pigneur, Business Model Generation, 2009, ISBN: 978-2-8399-050-0, as an important tool in the development process.

WP 8 will be run in 4 main activities as follows:

A) Develop a Business model for the implementation of the Vitae courses in the four countries (WP3)

B) Evaluate how well the model will work in each case (WP5 & WP7)

C) Analyse some successful cases for ICT teacher training courses

D) Work out the generic business model, i.e. a pattern that can be used for such models.

We will organise the work around the Business Model Canvas, that includes 9 modules:

a) Value Proposition; b) Key Activities; c) Key Partners; d) Key Resources; and e) Cost structures -

and f) Customer Relationships; g) Customer Segments h) Channels; and i) Revenue Streams

Expected outcomes: A generic business model (Pattern)

Quality management tools:

- For activity (A) of WP8: evaluation reports to evaluate the prototype of the business model and to give improvements guidance for the development of the final version of the business model;

- For activities (B, C and D ) of WP8:

2 set of evaluation reports as follows:

  - For Activity (B) - The first set of evaluation reports to evaluate the application of the prototype developed business model on the 4 EU countries, by the running of WP5, with the pilot VET training courses using the VITAE course in Portugal, Norway, Italy and Lithuania;

  - For Activities (C and D) - The second set of evaluation reports to evaluate the application of the final version of developed business model, after the final adjustments made on the business model, taking as input the first set of evaluation reports of WP8 and also the evaluation reports produced by WP5 (on its ninth activity (I)).

- Work package 9: Dissemination and exploitation

Aims:

To make public the results of the work done in the understand IT project both to managers, teachers, and researchers

To organize for a wide spread use of the Vitae approach by Learning centers, VET institutions and universities

Working methods: There are three elements necessary to obtain the first aim:

1) The Generic business model from WP 8

2) The Publication of the model, both in eLearning forums, but also at www.businessmodelgeneration.com

3) Development of a support service to support those institutions who will use the GBM Publications, conference talks, offering support to institutions adopting the GBM

Activities to obtain the first aim are:

- Publication of results through the NADE membership network

- Publication of results through the eTutor Portal

- Publication through the CoP developed in the Project

- Publication through the Web site for the project and the web sites for each Partner

- Publication through Papers and presentations at international conferences

Expected Outcomes: A set of Papers, conference presentations etc

- Paper/presentation in at least 2 important European conferences (i.e. EDEN, OEB, EADL)

- Presentation in a national conference in all/most partner countries

- Article in a European journal

- Article in a national journal in all/most partner countries

- Work package 10: Project management

Aims:

a) Be contractual partner versus SIU in Norway

b) Be contractual partner between HiST, AITeL and all the other partners

c) Make project results available through a project web site

d) Organise Partner meetings

d) Follow up progress and activities between the meetings

f) Implement a QAS for the project and evaluate the activities and results are according to defined QA standards

g) Follow up that expenditure is in accordance with the approved budget

h) Report to SIU on progress, products and other result

Working methods: Administration, accounting, communication, conflict resolution

Expected outcomes:

Interim and final reports

Project website

Quality management tools: These will be various and include

Finance: Templates for reporting costs and automated accountancy systems

Website: Statistics on visitors and their behavior

Project meetings: facilitated face to face discussion and structured questionnaires

Appendix 2: Evaluation of the Trondheim kick-off meeting 13-14 December 2010

More or less everyone filled in the questionnaire which is a very good result for something which was mainly done after the end of the meeting when we had all gone home.

Some of the questions are a result of my experience with other projects. So for example it seems that language is not an issue in UnderstandIT and I won't include that question in future evaluations. Similarly I have had to deal with a transition from project partners having high expectations on the free time and cultural events side to a more business-like approach. This explains the question about the balance between free time and meeting time. Again this does not seem to be an issue in this project so I would leave it out of future questionnaires.

The scores are generally very high so I think that we can be happy that this was a very successful meeting. The agenda and inclusiveness were especially high. One very important result was that everybody said that they were clear both about the project and their role in the project. This is excellent as I have experienced kick-off meetings where people leave more confused than when they arrived!

- Issues for attention are few

Scores are a little lower regarding information provided before the start of the meeting. This may be simply a common reaction to joining an unknown group but it may be an indicator that a bit more information is needed. It is also possible that people were not familiar with where they could find information and this will of course improve quickly now that we have started.

People also wanted:

- more training in the CCD room

- more experience with Adobe Connect

- more information about the VITAE courses

- more interaction with the Norwegian partners

- a forum (rather than email) and a web page

Some of these issues are being addressed eg the web page. Some cannot be addressed eg not all the Norwegian group will be attending future meetings but maybe we will get to know them better in the online meetings.

- Summary of 14 responses

| What was your overall impression of the meeting? |  |
| --- | --- |
| Did not meet my expectations; Exceeded my expectations. | Exceeded my expectations321%1071%17%00%1 - 5 - 4 3; Did not meet my expectations; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

Additional comments

- Everybody had a real engagement and a constructive attitude to seek for good ways to achieve the results.

- it was well organised.

Before the meeting

| Information about meeting venue and accommodation |  |
| --- | --- |
| Insufficient; Exceeded my expectations. | Exceeded my expectations536%750%214%00%1 - 5 - 4 3; Insufficient; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

Any other comments?

- Hopefully no loose ends?

- Would be good to collect all travel details, preparatory documents and other relevant info for the meeting on our project platform/google docs beforehand

| Information about the project before the meeting was |  |
| --- | --- |
| Insufficient; Exceeded my expectations. | Exceeded my expectations214%964%214%17%1 - 5 - 4 3; Insufficient; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

Additional comments

see above

| Information about preparatory work needed |  |
| --- | --- |
| Unclear; Clear. | Clear643%857%00%00%1 - 5 - 4 3; Unclear; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

Additional comments

During the meeting

| How do you rate your interaction with the other project partners and guests |  |
| --- | --- |
| There were some people I didn’t get to know well enough; I got to know the others as well as I needed. | I got to know the others as well as I needed536%536%429%00%1 - 5 - 4 3; There were some people I didn’t get to know well enough; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

| Was the agenda logical and comprehensive? |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| Do you feel you could influence the agenda if necessary? |  |
| --- | --- |
|  | 321%17%Yes Other; 10; 71%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| Did the meeting meet your communication needs regarding language? |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| Did you feel able to contribute to the meeting when you wanted to? |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| The CCeD taster session was |  |
| --- | --- |
| helpful; Un; Helpful. | Helpful750%536%214%00%1 - 5 - 4 3; Unhelpful; 0; 0%. 2. People may select more than one checkbox, so percentages may add up to more than 100%. |

Additional comments

But maybe it could, on future utilization on meetings like the UnderstandIT M1, be used from the first day, and by this way all partners get more used to the CCeD methodology, and specially get more ...

| Was the ratio of social events to working time reasonable? |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

At the end of the meeting

| I have a clear idea of the project as a whole. |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| I have a clear idea of my role in the project and my next steps. |  |
| --- | --- |
|  | 00%00%Yes Other; 14; 100%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

| I am familiar with the main communication channels to be used between project meetings. |  |
| --- | --- |
|  | 00%17%Yes Other; 13; 93%. No. People may select more than one checkbox, so percentages may add up to more than 100%. |

I wish that we had...

- some hours more to do some further training in the CCeD room.

- It would have been nice to go through a little session on Adobe, too.

- More time

- more time to work around with the current existing VITAE c...

I wish that we had not...

- didn't reach results.

Additional comments

- I strongly believe that with the good quality and achievements of this M1 the Project has started with the right steps to the success. but we need to work hard for it!

Anne Fox, WP7

11 January 2011

Appendix 3:  Some early WP results – the example of WP 10

- Contracts:

1)     With SIU, finalized and first payment received at HiST at the  17.12.2010 (x days after the contract was signed by SIU).

2)     HiST have issued contracts to all the partners at the first PM (kickoff). Some comments and suggestions for amendments / adjustments have come from: FHK (subcontracting); CENFIM ( reduced number of days because of higher cost per person than the figures used, subcontracting, travel to Rome missed out in the application); U o Rome (new person as legal representative), Anne Fox, travel and subsistence costs for the meeting in Copenhagen; HiST (sub contracting)

The contracts will be signed as they are, and the amendment will then be applied for in close collaboration with SIU.

Status per 5.01.11, all contracts received except for FHK.

- Project web site:

1)     For internal and working documents, Google docs and other Google tools will be used

2)     For external visibility a normal project web will be produced. A first version of this web site is to be released at the 15 th of January.

- Partner meetings:

PM1 (kickoff) in Trondheim 13.-14.12.2010

·         All partners were present

·         Run according to the agenda

·         The results and actions to be taken, described in the Minutes (to be released next week

·         Next meeting (PM2): 30.-31.5.2011 in Lisbon

·         Third meeting: (PM3): 13.-14.10.2011 in Copenhagen

- Net meetings:

·         7.01.11 – Test for communication to run Distributed Concurrent Design Sessions

·         21.01.11 – The first session in WP3

- Accounting:

·         Rules of accounting from Leonardo / SIU were presented at PM1

·         Forms used for reporting were presented and published at Google docs

·         The first accounting period: 26.9 – 31.12, to be sent to the coordinator will be the 15th of January 2011.

The “Survival Kit for European Project Management” (www.sokrates.at/survivalkit, 2001), which incorporates the experiences of a number of coordinators and evaluators of European projects.

The “Handbook Virtual Teamwork, making cooperation work in Leonardo da Vinci projects Information, theory and practical Tips”, published by the National Agency Leonardo da Vinci -The Netherlands 2004.

‘A project manager’s guide to evaluation’ by J Hughes and L Nieuwenhuis 2005

PAS 1032-1 Process for ensuring quality in e-learning